## Overview
Lab 8 — Product Lifecycle & Portfolio Intelligence
Merged project tracker · Figures on this tab are formulas and update as the other tabs change.
Project at a glance
Project | Acies AgenticBus — Lab 8: Product Lifecycle & Portfolio Intelligence
Purpose, as we understand it | A GTM demo asset that opens VP-level conversations with FMCG companies. Awaiting confirmation — Q1.
Opening problem | Slow decisions, poor product profitability visibility, missed rationalization opportunities, and disconnected market/customer signals.
Primary persona | VP Product Management / VP Portfolio Strategy
Secondary personas | Product Manager; Pricing & Margin Partner
Previous team | Amita, SreeVyshnavi, acies-Jai, Jaiadithya A — 369 commits, 18 May – 27 Jul 2026
Project start | 3 Sep 2026 (per team tracker)
Deadline | Not set (confirmed 22 Sep). The team tracker's 20 working days from 3 Sep is a placeholder. See Q9.
Current team | Guna
Programme owner
Live demo | ilp-ppl-dash-board.vercel.app
Tracker as of
Scope (team's problem understanding)
In scope | Portfolio health; launch readiness; product/SKU profitability; SKU rationalization; market/competitor/VoC signals; portfolio/product KPIs.
Out of scope | Full PLM engineering system; CAD; R&D/technical product development workflows; marketing campaign execution for launches.
Gates — earliest dates at planned durations
Gate 1 — End of SPS
Gate 2 — Solution design complete
Gate 3 — Functional prototype — five tabs without AI
Gate 4 — Final demo
Working days from today to Gate 4
Status
Activities in plan
Done
In progress
Rework needed
Not started
Blocked or at risk
Tab-rework activities still needing an estimate (3.2–3.6)
Activities with no owner yet
Open questions
Questions answered or defaulted
High-severity risks and issues not closed
Stakeholder meetings held
Gap-analysis items
Headlines
• | The database is live and reconciles to the source figures. The application does not read it yet — Backend (3.8) and Integration (3.9).
• | The team's functional review found 44 gaps across Portfolio Health, Launch Readiness and cross-module flow — including a revenue figure about 22× too high, now confirmed as a bug.
• | Five plans were in circulation. This tracker merges them; M8 should adopt it and retire the rest.
• | No deadline is set. Gate 4 above is the earliest date at the plan's durations, and it is optimistic: tab rework (3.2–3.6) has no estimates yet.
• | TODO.md (the dev-level tracker, separate from this Project Plan) stood at 30 Sep 2026: 12 of 17 tracked phases Done, 2 partly done, 2 open, 1 decided (~71%). By checkbox count 19/53 (~36%) — lower because most completed phases (schema, dataset generation, the database, branding) were logged as narrative/tables rather than checkboxes, while nearly all remaining open work is checkbox-tracked, so the checkbox ratio understates progress.
What this tracker replaces
• | The 16-phase plan (screenshot) — including a 'Core CRM Modules' row that does not apply to this product.
• | The team tracker's Project Tracker, Project Internal Tracker and Action Plan tabs — their content is merged here.
• | The first version of this tracker.
Tabs
Project Plan | P0–P4 with Gates 1–4. Owner, status, dates, dependencies, definition of done. Source column shows where each row came from.
Open Questions | The 15 decisions we need, each with a recommendation and a default.
Stakeholder Meetings | Meetings M1–M8 and the questions each settles.
Gap Analysis | The team's 44 functional gaps, each mapped to a plan step.
Personas & Journey | Who needs what; current → future journey; the end-to-end decision journey.
Risks & Issues | What could go wrong or already has, with severity.
Decisions | Decisions made, why, and when to revisit.
Architecture Roadmap | How we get from today's architecture to the target.
Research & Data | Our research and the team's; the dataset we built and its gaps.
Handover Findings | The condition of what we received — the reverse-KT agenda.
Timeline | What happened and when.
Benchmark | The team's PLM vendor comparison, with caveats.
Links | Every document, repository and the live demo.
Legend
Light-yellow cell | Please fill in or confirm — including role names to replace with people
Blue text | Typed input — dates and durations you can change
Black text | Formula or fixed text — do not overwrite formulas
Grey italic date | Tentative — computed from durations; moves when an input changes
Shaded row | A gate — its date is the latest end of the activities before it

## Project Plan
Project Plan — merged
Backbone: the team tracker's P1–P4 phases and Gates 1–4. Our workstreams merged in and marked by source. Blue = typed input · black = formula · light yellow = please fill in · grey italic = tentative date.
ID | Phase | Type | Activity | Source | Objective | Key question | Owner | Status | Days (working) | Start | End | Date basis | Depends on | Expected outcome / definition of done | Where it actually stands | Evidence
0.1 | P0 · Handover & remediation | Activity | Knowledge transfer (KT) and reverse KT | Original 16-phase plan | Receive the existing application from the previous team, then play our understanding back. | Have we understood the product, its data and its personas the way the previous team intended? |  | In progress | 5 |  |  | To confirm | — | RKT held; previous team confirms our understanding; handover gaps logged. | KT completed before the first commit on 1 Sep. RKT not yet held — Handover Findings is its agenda (meeting M5). | Handover Findings tab
0.2 | P0 · Handover & remediation | Activity | Codebase remediation | Added | Make the inherited code safe to change before building on it. | Can we change the code without breaking what already works? | Guna | Done |  | 2026-09-01 | 2026-09-20 | Actual (git) | 0.1 | Type check and build clean; 27/27 smoke; no debris in the repository root. | 187 files removed; nine files of 22,619 lines split into 30 modules (−47%); 1,237 invalid colour classes fixed; dead Express server and 124 unused npm packages removed. | Commits 1–20 Sep; TODO.md
1.1 | P1 · Business Understanding & SPS | Activity | Understand current problem statement | Team tracker | Understand the business problem, scope, personas, expected outcomes and terminology in the brief. | What problem are we solving? Who is affected? What is explicitly in/out of scope? | Team Lead | In progress |  | 2026-09-03 |  | Start per team tracker; ends at stakeholder sign-off | — | Initial problem understanding; agreed terminology; open questions | Problem, personas and scope written up (Overview → Scope). Four problem areas still need ranking — Q14. | Team tracker; pitch.md
1.2 | P1 · Business Understanding & SPS | Activity | Map current-state problem | Team tracker | Translate the stated problem into a current-state process and identify where delays/manual work occur. | Where does data come from? Where are decisions delayed? Where are workarounds used? | Business Analyst | In progress |  |  |  | Tentative — ends at stakeholder sign-off | — | As-Is process map + pain-point map | Current → future decision journey drafted, plus an end-to-end journey in Miro. Pain points listed but not yet validated. | Personas & Journey tab
1.3 | P1 · Business Understanding & SPS | Activity | Identify and validate personas | Team tracker | Understand the needs of VP Product Management, Product Manager and Pricing/Margin Partner. | What does each persona decide? What information does each need? | Business Analyst | Done |  |  |  | Tentative — ends at stakeholder sign-off | 1.7 | Persona + decision + KPI matrix | Persona x capability matrix validated at the code level: a tab-by-tab audit ('Nine Tabs, Zero Backend', 23 Sep) confirmed only the VP has a dedicated view anywhere, and found Product Manager -- marked primary on Launch Readiness -- is silently routed into the VP's own screen. A working prototype now reorders the sidebar per role from this same matrix, verified on all three roles. Both are evidence for M3, not yet signed off (Q7). | Personas & Journey tab; Report 2
1.4 | P1 · Business Understanding & SPS | Activity | Build diagnostic issue tree | Team tracker | Break the broad portfolio problem into measurable problem areas and hypotheses. | What are the possible root causes behind slow launches, poor profitability, rationalization gaps and disconnected signals? | Business Analyst | Not started | 2 | 2026-09-23 |  | Tentative — our estimate | — | Issue tree + hypotheses | Not started. Handover Findings covers code-level causes; business root causes are still hypotheses. | —
1.5 | P1 · Business Understanding & SPS | Activity | Secondary research | Team tracker | Research portfolio management, SKU rationalization, launch readiness, profitability and AI applications. | What industry practices and benchmarks can validate/refine the problem? | Research Owner | Done |  |  | 2026-09-17 | Actual end | — | Research notes + evidence | Report 3 (FMCG intelligence vendors) and the team's PLM benchmark cover it between them. | Report 3; Benchmark tab
1.6 | P1 · Business Understanding & SPS | Activity | SPS synthesis | Team tracker | Convert research and stakeholder findings into an evidence-backed problem statement. | What is the specific root cause? Which pain point is most important? | Team Lead | Not started | 1 |  |  | Tentative — our estimate | 1.4, 1.7 | SPS findings + validated problem statement | Waits on stakeholder answers. | —
1.7 | P1 · Business Understanding & SPS | Activity | Stakeholder alignment on scope (M1–M4) | Added | Settle scope, metrics, tabs and delivery with the people who own them. | Is this a demo asset or a product, and what does the brief really require? |  | Not started | 4 | 2026-09-23 |  | Tentative | — | M1–M4 held; every open question answered or defaulted. | Not yet scheduled. Every tentative date after this row assumes it finishes on the date shown. | Stakeholder Meetings tab
G1 | P1 · Business Understanding & SPS | Gate | Gate 1 — End of SPS | Team tracker | Validated problem + issue tree + personas + research findings | — |  | Not started |  |  |  | Tentative | 1.1–1.7 | Validated problem + issue tree + personas + research findings | — | —
2.1 | P2 · Solution Definition | Activity | Define decision journeys | Team tracker | Define the decisions the solution should support from the perspective of each persona. | What decision should the user make after seeing the insight? | Business Analyst | In progress | 1 |  |  | Tentative — our estimate | G1 | Decision journey map | Draft exists (Miro journey). Missing: the closed loop from decision to measured impact. | Personas & Journey tab
2.2 | P2 · Solution Definition | Activity | Define five functional modules | Team tracker | Translate the brief into the five required domain modules and their business questions. | What should each tab show and what decision does it enable? | Product Owner | In progress | 1 |  |  | Tentative — our estimate | G1, Q7 | Module requirements matrix | Report 2 recommends the brief's five modules; sign-off pending (Q7). | Report 2
2.3 | P2 · Solution Definition | Activity | Define KPI framework | Team tracker | Define KPI meaning, calculation approach, grain, source and target/benchmark assumptions. | How will Margin, Time-to-Market, Launch Success, SKU Productivity, Complexity and Cannibalization be measured? | Analytics Lead | In progress | 2 |  |  | Tentative — our estimate | G1, Q2–Q5 | KPI dictionary | Report 1 defines every metric. Open: the revenue baseline (Q2); two KPIs with no data (Q3); unsupported cards (Q4, Q5). | Report 1
2.4 | P2 · Solution Definition | Activity | Define data requirements | Team tracker | Identify product, sales, cost, supply, launch, market, customer and competitor data needed. | What fields, granularity and refresh frequency are required? | Guna | Done |  |  | 2026-09-14 | Actual end | — | Data requirement matrix | 13-table star schema specified with types and keys. | data_model_specification.md
2.5 | P2 · Solution Definition | Activity | Define business rules | Team tracker | Create transparent decision logic for readiness, profitability alerts and rationalization. | What conditions trigger GO/REVIEW/DELAY or retain/grow/bundle/reposition/sunset? | Analytics Lead | Not started | 2 |  |  | Tentative — our estimate | 2.3, Q13 | Business rule catalogue | Blocked until one decision vocabulary is agreed (Q13). | —
2.6 | P2 · Solution Definition | Activity | Define Now vs AI-Assisted vs Agentic | Team tracker | Define where automation, AI assistance and agent orchestration add value. | What should remain human-led? What can AI analyze? What can agents monitor/recommend? | AI Lead | In progress | 1 |  |  | Tentative — our estimate | G1 | AI/Agentic evolution map | Now / Next / Future architecture drawn; the rule 'the LLM explains, never computes' is proposed (Q10). | system_architecture.md
2.7 | P2 · Solution Definition | Activity | Solution architecture and hosting | Original 16-phase plan | Agree the technical architecture and where each part runs. | What runs where, and what does it cost? |  | In progress | 2 |  |  | Tentative — original plan (0.3 week) | G1, Q10 | Target architecture and hosting agreed. | Stack decided: PostgreSQL, Python / FastAPI, metrics in SQL. Hosting and LLM budget open (Q10). | Architecture Roadmap tab
2.8 | P2 · Solution Definition | Activity | UI/UX design for the five domain tabs | Original 16-phase plan | Lay out the five domain tabs for each persona, using the gap analyses as requirements. | Does each tab lead its persona from insight to decision? |  | Not started | 3 |  |  | Tentative — original plan (3 days) | 2.2 | Approved layouts for five tabs × three personas. | The design system exists; this is consolidation, not a fresh visual design. A first prototype (persona-ordered sidebar, App.tsx) is built and verified but not committed -- draft input for this step, not a substitute for it. | Gap Analysis tab
G2 | P2 · Solution Definition | Gate | Gate 2 — Solution design complete | Team tracker | Five modules + KPI dictionary + data model + business rules | — |  | Not started |  |  |  | Tentative | 2.1–2.8 | Five modules + KPI dictionary + data model + business rules | — | —
3.1 | P3 · Data & Prototype | Activity | Create simulated data model | Team tracker | Create realistic linked datasets for products/SKUs, sales, costs, supply, launches, market and VoC. | Can the data support every required module and KPI? | Guna | Done |  | 2026-09-09 | 2026-09-14 | Approx. start (seed date); actual end | — | Validated prototype dataset | 119 SKUs × 7 countries × 4 channels × 731 days; 368,013 fact rows; 16 of 16 validation targets met. | Research & Data tab
3.1a | P3 · Data & Prototype | Activity | Load the PostgreSQL warehouse | Added | Put the dataset into a real database the application can read. | Do the loaded totals reconcile? | Guna | Done |  | 2026-09-14 | 2026-09-20 | Actual | 3.1 | 13 tables loaded; totals match the generator. | 377,364 rows loaded 20 Sep. Reconciles: $473.0M net sales, +8.29% growth, 38.55% margin. | data/schema/
3.1b | P3 · Data & Prototype | Activity | Derived-metric SQL and SQL validation | Added | Give every formula a single implementation, in SQL. | Do the 16 checks pass in SQL too? |  | Not started | 2 |  |  | Tentative — our estimate | 3.1a, Q2 | Derived tables rebuilt in SQL; 16 checks pass in SQL. | 03_derive_metrics.sql and 04_validate.sql. | TODO.md O2
3.1c | P3 · Data & Prototype | Activity | Metric integrity and data wiring | Added | One value per metric on every screen. | Does any figure disagree between screens? |  | In progress | 5 |  |  | Tentative — our estimate | 2.3, Q2, Q4, Q5 | Each metric has one value everywhere; no empty KPI strip; lifecycle revenue bug fixed. | Every formula in the app catalogued and verified against source (documentation/formulas.md, 23 Sep) -- Python generator, SQL, and all 9 tabs, each marked real / real-formula-fake-input / fabricated. New finding: the timeline selector fabricates variance on every figure it touches, including the two KPI-strip metrics this review had called genuinely computed (R22). The audit is complete; the actual rewiring and fixes have not started. | TODO.md O7
3.1d | P3 · Data & Prototype | Activity | Replace real brands with fictional ones | Added | Remove trademark exposure from the demo. | Could a client recognise a real brand on screen? |  | Not started | 1 |  |  | Tentative — our estimate | Q8 | No real brand names in data, screens or simulator. | Seven real brands in the database, plus Pepsi, Mountain Dew and Lay's in the pricing simulator. Needs a dataset regenerate and reload. | TODO.md O9
3.2 | P3 · Data & Prototype | Activity | Rework Portfolio Health Map | Team tracker (reworded: tab exists) | Build lifecycle, growth, revenue, margin and strategic-fit views. | Can the VP identify healthy and underperforming products quickly? | UI/BI Lead | Rework needed |  |  |  | Tentative — needs an estimate | G2 | Functional Tab 1 | Tab exists. 21 gaps identified in the team's functional review. | Gap Analysis tab
3.3 | P3 · Data & Prototype | Activity | Rework Launch Readiness Dashboard | Team tracker (reworded: tab exists) | Build market, supply, channel and pricing readiness views. | Can the user identify launch risks and readiness status? | UI/BI Lead | Rework needed |  |  |  | Tentative — needs an estimate | G2 | Functional Tab 2 | Tab exists. 15 gaps identified. The Product Manager is served the VP's view, but the persona matrix makes PM primary here. | Gap Analysis tab
3.4 | P3 · Data & Prototype | Activity | Rework Profitability Tree | Team tracker (reworded: tab exists) | Build revenue, margin, cost-to-serve and leakage analysis. | Can the user explain why profitability is changing? | Analytics/UI Lead | Rework needed |  |  |  | Tentative — needs an estimate | G2 | Functional Tab 3 | Tab exists. No gap analysis yet — next for the team. | —
3.5 | P3 · Data & Prototype | Activity | Rework SKU Rationalization Simulator | Team tracker (reworded: tab exists) | Build retain/grow/bundle/reposition/sunset recommendations and scenario impact. | Can the user simulate portfolio changes and see revenue/margin/complexity impact? | Analytics/UI Lead | Rework needed |  |  |  | Tentative — needs an estimate | G2, Q13 | Functional Tab 4 | Tab exists. No gap analysis yet. Outcome labels differ from the team's (Q13). | —
3.6 | P3 · Data & Prototype | Activity | Rework Market & VoC Signal Board | Team tracker (reworded: tab exists) | Build customer sentiment, competitor, demand and channel signal views. | Can external signals influence portfolio decisions? | UI/BI Lead | Rework needed |  |  |  | Tentative — needs an estimate | G2, Q11 | Functional Tab 5 | Tab exists. No gap analysis yet. Competitor content is authored, not fed (Q11). | —
3.7 | P3 · Data & Prototype | Activity | Consolidate 12 tabs into 5 | Original 16-phase plan (Frontend 'Done' → rework) | Fold Home, Top-Down Drill, Assortment, Orchestrator and Task Tracker into the five domain tabs. | Can each persona do their job in five tabs? |  | Not started | 10 |  |  | Tentative — our estimate | 2.8, Q7 | Five domain tabs live; duplicated VP / standard views unified; smoke test covers every tab. | 12 tabs today. The decision journey shows the drill-down belongs inside each tab. | TODO.md O8
3.8 | P3 · Data & Prototype | Activity | Backend — FastAPI read API and metric registry | Original 16-phase plan | Serve every displayed figure from PostgreSQL through one metric registry. | Does every figure on screen have one definition and one source? |  | Not started | 30 |  |  | Tentative — original plan (6 weeks) | 2.3, 2.7, 3.1a | Read API serves every displayed figure from the registry. | Critical path. Nothing built yet. If Q1 = demo asset, read-only endpoints are enough. | requirements.txt
3.9 | P3 · Data & Prototype | Activity | Integration — the app reads from the API | Original 16-phase plan | Replace constant imports with one data hook calling the API. | Is any figure still hardcoded? |  | Not started | 5 |  |  | Tentative — original plan (1 week) | 3.7, 3.8 | No figure imported from a constant file. | Nothing in the app calls a server today. | —
G3 | P3 · Data & Prototype | Gate | Gate 3 — Functional prototype | Team tracker | Five tabs working without AI dependency | — |  | Not started |  |  |  | Tentative | 3.1b–3.9 | Five tabs working without AI dependency | Excludes 3.2–3.6 until they have estimates, so this date is optimistic (R21). | —
4.1 | P4 · AI, Testing & Final Demo | Activity | Design agent responsibilities | Team tracker | Refine Portfolio, Market Signal, Launch, Profitability and Sunset agent roles. | What does each agent monitor, analyze, recommend and hand off? | AI Lead | Not started | 2 |  |  | Tentative — our estimate | G2, Q15 | Agent responsibility matrix | Five agents named in the brief; today's widget is keyword matching. | —
4.2 | P4 · AI, Testing & Final Demo | Activity | Implement agentic recommendations | Team tracker | Connect agents to business rules/data and generate explainable recommendations. | Do recommendations lead to an actionable decision? | AI/Tech Lead | Not started | 5 |  |  | Tentative — original plan (1 week) | 3.8, 4.1, Q10 | Agent-enabled prototype | No model is called today. | —
4.3 | P4 · AI, Testing & Final Demo | Activity | End-to-end scenario testing | Team tracker | Test a complete portfolio/launch/rationalization scenario from signal to decision. | Can a VP move from insight to action in one flow? | QA + Product | Not started | 3 |  |  | Tentative — original plan (testing, 1 week) | G3, 4.2 | Validated end-to-end scenario | Foundations: 16 data checks and a browser smoke test (27/27). Tabs 9–11 are not smoke tested. | scripts/smoke.mjs
4.4 | P4 · AI, Testing & Final Demo | Activity | UX and KPI validation | Team tracker | Check usability, KPI correctness, assumptions and consistency across tabs. | Are the outputs understandable and defensible? | QA Lead | Not started | 2 |  |  | Tentative — original plan (testing, 1 week) | 4.3 | QA checklist + fixes | — | —
4.5 | P4 · AI, Testing & Final Demo | Activity | Final demo storyline | Team tracker | Create a 10–15 minute VP-focused journey from problem to recommendation and outcome. | Does every tab earn its place and support a decision? | Team Lead | Not started | 2 |  |  | Tentative — our estimate | 4.4, Q9 | Final demo script + slides | Use the end-to-end decision journey as the script. | Personas & Journey tab
4.6 | P4 · AI, Testing & Final Demo | Activity | Final review and handover | Team tracker | Close open issues, document assumptions and prepare final submission. | What remains unresolved? Are all scope/KPI/agent requirements covered? | Team Lead | Not started | 2 |  |  | Tentative — our estimate | 4.5, 4.7 | Final prototype + documentation | — | —
4.7 | P4 · AI, Testing & Final Demo | Activity | Deployment | Original 16-phase plan | Host the frontend, API and database for the demo. | Is the demo URL stable and the data current? |  | Not started |  |  |  | Tentative — needs a duration (original: TBD) | 4.4, Q10 | Frontend, API and database hosted; demo URL stable. | Frontend on Vercel as a static site. Enter a duration in column J to schedule it. | Links tab
G4 | P4 · AI, Testing & Final Demo | Gate | Gate 4 — Final demo | Team tracker | Agents + simulation + testing + VP decision journey | — |  | Not started |  |  |  | Tentative | 4.1–4.7, Q9 | Agents + simulation + testing + VP decision journey | No deadline set (confirmed 22 Sep). This is the earliest date at the durations above. | —
4.8 | P4 · AI, Testing & Final Demo | Activity | Enhancement / production roadmap | Original 16-phase plan | Plan what comes after the demo. | What does the agreed positioning need next? |  | Not started |  |  |  | Tentative (original: TBD) | G4, Q1 | Roadmap agreed for the chosen positioning. | Depends on Q1 — a demo asset and a product have very different roadmaps. | —
Formulas:
End = IF(OR([Start]="",[Days (working)]=""),"",WORKDAY([Start],[Days (working)]-1))
Days (working) = IF(OR([Start]="",[End]=""),"",NETWORKDAYS([Start],[End]))
Start = WORKDAY(MAX(L10,[End, row below]),1)
Start = WORKDAY([End, row above],1)

## Daily Task Log
Daily Task Log
Retrospective — every entry below is completed work, logged after the fact. No formal daily plan existed before this sheet, so Planned EOD equals Actual EOD throughout; going forward, set Planned EOD before the day starts.
Date | Team Member | Workstream / Module | Task / Activity | What Needs to Be Done | Status | Priority | Dependency / Blocker | Planned EOD | Actual EOD | Remarks
18 May 2026 | Jaiadithya A / acies-Jai | Frontend Build | Repository and application scaffold | Stand up the React/Vite/Tailwind shell, 3-persona welcome gate, initial tab routing | Done | High | None | — | 20 May 2026 | Inherited — first commits of the project
21 May – 27 Jul 2026 | Amita, SreeVyshnavi, acies-Jai | Frontend Build | Build all 12 tabs, KPI cards, simulators, agent widget | Deliver the full dashboard surface: Portfolio Health, Launch Readiness, Profitability, SKU Rationalization, Signals, plus supporting modals | Done | High | None | — | 27 Jul 2026 | 369 commits, 4 contributors — compressed to one row; see Timeline tab for detail. Repository then idle 27 Jul – 1 Sep.
1 Sep 2026 | Guna | Codebase Remediation | Restore type safety, split bundle, extract shared primitives | Re-enable TypeScript checking (bypassed by the previous team); break up the monolithic bundle | Done | High | None | 1 Sep 2026 | 1 Sep 2026 | First commit of the remediation phase
1 Sep 2026 | Guna | Codebase Remediation | Repair 1,237 invalid Tailwind colour classes | Fix broken utility classes across 63 files so styling actually applies | Done | Medium | None | 1 Sep 2026 | 1 Sep 2026
1 Sep 2026 | Guna | Codebase Remediation | Route all 43 overlays through shared modal primitives | Deduplicate modal/overlay implementations onto one shared component set | Done | Medium | None | 1 Sep 2026 | 1 Sep 2026
9 Sep 2026 | Guna | Dataset Generation | Search for a usable real dataset | Determine whether real transaction-level data exists to ground the app's metrics | Done | High | None | 9 Sep 2026 | 9 Sep 2026 | None found — only aggregate notebook outputs. Decided to generate a synthetic dataset instead (Decision D1).
14 Sep 2026 | Guna | Dataset Generation | Build and validate the synthetic FMCG dataset | Generate 119 SKUs x 7 countries x 4 channels x 2 years, seeded, reconciling to the source figures | Done | High | Dataset search (row above) | 14 Sep 2026 | 14 Sep 2026 | 368,013 fact rows; 16 of 16 validation targets met
14 Sep 2026 | Guna | Documentation | Write data model specification and generation plan | Document the 13-table schema (types, keys, grain) and the generation rules before building the database | Done | High | None | 14 Sep 2026 | 14 Sep 2026
17 Sep 2026 | Guna | Product Research | Publish Report 1 — Metric Dictionary | Define every displayed metric and justify why it's calculated | Done | High | None | 17 Sep 2026 | 17 Sep 2026 | Found only 2 of 6 required KPIs properly computed
17 Sep 2026 | Guna | Product Research | Publish Report 2 — Twelve Tabs to Five | Audit all 12 tabs per persona and recommend which to keep | Done | High | None | 17 Sep 2026 | 17 Sep 2026
17 Sep 2026 | Guna | Product Research | Publish Report 3 — Worth Building? | Assess the competitive landscape and whether this is worth building | Done | Medium | None | 17 Sep 2026 | 17 Sep 2026
20 Sep 2026 | Guna | Codebase Remediation | Repo cleanup, phases A–C | Remove scratch files and dead code; split 9 oversized files into 30 modules | Done | High | None | 20 Sep 2026 | 20 Sep 2026 | 187 files removed; 22,619 -> 11,854 lines (-47%)
20 Sep 2026 | Guna | Codebase Remediation | Delete dead Express server and unused dependencies | Confirm the backend language (Python/FastAPI) and remove the Node backend remnants | Done | Medium | Backend language decision | 20 Sep 2026 | 20 Sep 2026 | 124 npm packages removed
20 Sep 2026 | Guna | Database Setup | Create PostgreSQL role and database; build the 13-table schema | Stand up ppl_intelligence with a least-privilege application role | Done | High | Postgres superuser password | 20 Sep 2026 | 20 Sep 2026 | Fixed two real psql scripting bugs along the way
20 Sep 2026 | Guna | Database Setup | Load the generated dataset into PostgreSQL | COPY all 13 tables in FK order and reconcile against the generator's targets | Done | High | Schema built (row above) | 20 Sep 2026 | 20 Sep 2026 | 377,364 rows loaded in 44.9s; reconciles to $473.0M / +8.29% / 38.55%
20 Sep 2026 | Guna | Architecture & Planning | Draw Now / Next / Future system architecture | Document the current state, the trustworthy-demo target, and the long-term agentic target | Done | Medium | None | 20 Sep 2026 | 20 Sep 2026 | Excalidraw-ready Mermaid diagrams
21 Sep 2026 | Guna | Stakeholder Prep | Draft stakeholder pitch and 12 open questions | Turn the three reports into a decision-ready document with a recommendation and a default per question | Done | High | Reports 1-3 | 21 Sep 2026 | 21 Sep 2026
22 Sep 2026 | Guna | Project Tracking | Build the merged project tracker | Combine the team's P1-P4 plan, gap analyses and persona matrix with our data and architecture work into one tracker | Done | High | Team tracker reviewed | 22 Sep 2026 | 22 Sep 2026 | Replaced 5 competing plans in circulation
23 Sep 2026 | Guna | Persona / UI Audit | Publish the 'Nine Tabs, Zero Backend' tab audit | Check what's built, real vs. fabricated data, and backend status for every tab and persona | Done | High | None | 23 Sep 2026 | 23 Sep 2026
23 Sep 2026 | Guna | Persona / UI Audit | Prototype persona-specific sidebar ordering | Reorder the 9 sidebar tabs per role using the persona matrix; revert the earlier landing-page change | Done | Medium | Tab audit (row above) | 23 Sep 2026 | 23 Sep 2026 | Found and logged a real bug: role does not update on hashchange (TODO.md O10)
23 Sep 2026 | Guna | Metric Integrity Audit | Catalogue every formula in the application | Verify each displayed metric against source: real, real-formula-fake-input, or fabricated | Done | High | None | 23 Sep 2026 | 23 Sep 2026 | Found the timeline selector fabricates variance on every figure, including the 2 metrics previously found genuinely computed
24 Sep 2026 | Guna | Project Tracking | Update tracker with completed-task status | Reflect progress on personas (1.3) and metric integrity (3.1c); log the timeline-noise finding as a new risk (R22) | Done | Medium | Formula audit (row above) | 24 Sep 2026 | 24 Sep 2026 | Fixed a column-shift bug from this same edit
25 Sep 2026 | Guna | Project Tracking | Add this daily task log | Add a per-day task log in the team's own tracking format | Done | Low | None | 25 Sep 2026 | 25 Sep 2026 | This sheet
29 Sep 2026 | Guna | Database Integration | O1 threshold audit — dollar-cutoff calibration | Decide and implement how hand-tuned dollar thresholds (Netherlands / France-Austria-Poland catalog cutoffs, Introduction-stage lifecycle cutoff) should be rescaled now that real per-SKU revenue is live — verify selectivity is preserved, not just unit-converted | Done | High | Live SKU revenue (skuRevenueM) | 29 Sep 2026 | 29 Sep 2026 | Mean-ratio rescale was wrong for SKUHoldingsMatrix — real revenue is Pareto-skewed vs. the old uniform hand-typed values; caught by checking selectivity numerically, fixed with rank-preserving constants instead
30 Sep 2026 | Guna | Branding / UI | Extract and wire the product logo | Crop the cube mark from the reference Logo.png, produce header / login / favicon assets, replace placeholder icons in Header, LoginPage and WelcomeGate | Done | Medium | Logo.png reference image | 30 Sep 2026 | 30 Sep 2026 | Also replaced WelcomeGate’s generic "AI network lines" background with a product-lifecycle-curve motif matching the brand
30 Sep 2026 | Guna | UI / Navigation | Convert "Switch profile" into an inline dropdown | Replace the full-screen navigate-back-to-Welcome-Gate flow with an in-header role picker so switching persona no longer leaves the current tab | Done | Medium | None | 30 Sep 2026 | 30 Sep 2026 | Removed the now-dead handleSwitchPersona / onSwitchPersona plumbing it replaced
30 Sep 2026 | Guna | Product Research | Review daily team call; audit Top-Down Drilldown against the database | Check whether the OTIF / fulfillment drill-down (LATAM / EMEA / APAC) the team reviewed live on the call is backed by real data | Done | High | Database connected (29 Sep) | 30 Sep 2026 | 30 Sep 2026 | Found the regions, managers and OTIF numbers shown are entirely fictional — the DB only has 7 European countries; real lead-time / stockout signals exist but are not wired to this screen
30 Sep 2026 | Guna | Product Research | Decide real vs. illustrative regions for the drill-down | Choose whether Top-Down Drilldown should be relabeled to the DB’s real 7 countries / 3 European regions, or stay APAC / EMEA / LATAM as demo framing | Not started | High | Team decision | — | — | Blocks defining a real OTIF metric; raised in the 30 Sep call
30 Sep 2026 | Guna | Metrics / Backend | Define and compute a real OTIF metric | fact_sales only has stock_out_flag and lead_time_days, not literal ordered-vs-received quantities — pick a derivable definition and add it as a SQL function, same pattern as the other live metrics | Not started | High | Region decision (row above) | — | — | Raised in the 30 Sep call as the model for detect → diagnose → simulate → recommend elsewhere in the app
30 Sep 2026 | Guna | Frontend / Search | Bulk multi-SKU search and combined report | Let a user select several SKUs at once (not just one at a time) and generate a single combined report | Not started | Medium | None | — | — | Confirmed missing app-wide; raised in the 30 Sep call
30 Sep 2026 | Guna | Frontend | Report download / export | Confirm and, if missing, add a way to download what is on screen — currently only scattered per-tab CSV buttons exist (SKU Performance, Rationalization) | Not started | Medium | None | — | — | Left as an open question in the 30 Sep call
30 Sep 2026 | Guna | Codebase Remediation | O1 threshold audit — percent constants | Wire the hand-tuned % constants (cannibalization uplift, waste write-off, complexity savings, etc.) to live revenue inputs; the constants themselves stay as-is per the 29 Sep decision | Not started | Medium | Live skuRevenueM in the affected files | — | — | Decided 29 Sep: treat as demo-plausible assumptions, no recalibration needed — just needs wiring

## Open Questions
Open Questions — decisions we need
Each has a recommendation, so 'agreed' is a complete answer. 'Needed by' follows the meeting date. Light yellow = please fill in.
# | Question | Why it matters | Options | Recommendation | Default if unanswered | Who answers | Meeting | Needed by | Status | Answer / decision
Q1 | Is Lab 8 a capability showcase or a product that competes? | Decides investment in ingestion, security and competitor data. | A · GTM demo asset B · Internal accelerator C · Product | A, keeping B open | Build as a GTM demo asset | Programme owner | M1 |  | Open
Q2 | Which revenue baseline is canonical — $473M or $851M? | Every downstream figure and the metric registry depend on it. | $473M (validated dataset) $851M (in more places — 18 source lines) | $473M | $473M | Programme owner; finance SME | M2 |  | Open
Q3 | Two required KPIs — time-to-market and launch success — have no data. 0 of 119 SKUs have a launch date. | 2 of the 6 required KPIs cannot be computed; the launch closed loop needs the same data. | Synthetic launch table Drop both KPIs Source real launch data | Synthetic launch table (~2 days) | Add a synthetic launch table | Programme owner | M2 |  | Open
Q4 | Gross Profit, Net Profit and SG&A cards have no cost basis — no opex columns exist. | An undefendable profit figure is the likeliest thing to end a client demo badly. | Remove the cards Extend the model with opex | Remove | Remove the three cards | Programme owner; finance SME | M2 |  | Open
Q5 | 12 of 20 designed metrics have no value. Compute or remove? | KPI strips render empty on four tabs. | Compute those the data supports Delete the rest | Compute what maps; delete the rest | Compute what maps; delete the rest | Programme owner | M2 |  | Open
Q6 | Netherlands margin: the source says lowest (38.20%); our data says highest (40.27%). Which is right? | Credibility with an informed viewer; a gap in our validation. | Source is right — fix generator, add a check Source was an artefact | Treat the source as authoritative | Fix the generator; add a validation check | FMCG / finance SME | M2 |  | Open
Q7 | Which five tabs? And should the Product Manager see the VP's Launch Readiness view? | Gates UI/UX and the tab consolidation. | The brief's five modules as named in the team tracker (3.2–3.6) | Adopt those five; fold Home, Top-Down Drill, Assortment, Orchestrator and Task Tracker into them. Give the PM its own launch view — the persona matrix makes PM primary there. | None — needs an owner | Programme owner | M3 |  | Open
Q8 | Rename the real brands in the demo? | Seven real brands in the SKU list; Pepsi, Mountain Dew and Lay's in the pricing simulator. | Rename all to fictional brands Keep competitor names as labelled references | Rename all | Rename all | Programme owner | M3 |  | Open
Q9 | When is the first demo, and to whom? | No deadline is set (confirmed 22 Sep). The team tracker's 20 working days from 3 Sep (to 30 Sep) is a placeholder. | — | Set a date; the Overview shows the earliest at planned durations | None — needs an owner | Programme owner | M1 |  | Open
Q10 | Where does it run, what is the LLM budget, and is 'the LLM explains, never computes' agreed? | Backend hosting, agent design and running cost. | — | Agree the principle; re-price models before quoting | None — needs an owner | Programme owner; budget holder | M4 |  | Open
Q11 | Does the Signals Board need a real competitor feed? | A second data source with its own grain, refresh and licensing. | Illustrative, clearly labelled Real feed | Illustrative if Q1 = A | Keep illustrative, labelled | Programme owner | M1 |  | Open
Q12 | Is the repository public? | A database password is in pushed git history (a3a3c54). It protects nothing today, but the follow-up depends on visibility. | — | Confirm visibility | Treat as private; value already rotated | Guna | M4 |  | Open
Q13 | Which words do we use for decisions? | SKU outcomes appear three ways and launch decisions two ways across the team tracker and the app. Business rules (2.5) cannot be written until one set is chosen. | SKU: Retain / Optimize / Reposition / Discontinue · retain / grow / bundle / reposition / sunset · app: Keep / Grow / Consolidate / Rationalize Launch: GO / CONDITIONAL GO / NO-GO · GO / REVIEW / DELAY | Keep the app's four segments as the classification; use Retain / Optimize / Reposition / Discontinue as the decision, and GO / CONDITIONAL GO / NO-GO for launches | As recommended | Programme owner; FMCG SME | M2 |  | Open
Q14 | Which problem is most acute, and which module should the demo lead with? | Decides where rework effort goes first. From the team's validation tracker (problem and priority module). | Portfolio Health · Profitability · SKU Rationalization · Launch Readiness · Signals | Lead with Portfolio Health — VP-primary, and where the decision journey starts | Lead with Portfolio Health | Programme owner | M1 |  | Open
Q15 | Which agent decisions may be automated, and which only recommended? | Decides agent design (4.1). From the team's validation tracker (agentic scope). | Recommend only Automate low-risk alerts Automate actions | Agents detect and recommend; a person approves every action | Recommend only | Programme owner | M4 |  | Open

## Stakeholder Meetings
Stakeholder Meetings — clearing scope and misunderstandings
Schedule M8 and M1 first. Light yellow = please fill in.
# | Meeting | Purpose | Questions to settle | Suggested attendees | Pre-read | Proposed date | Length | Status | Decisions / outcome
M8 | Team plan alignment | Adopt this merged tracker as the only plan; put names against roles; estimate 3.2–3.6. | D13, R19, R21 | Project team | This tracker |  | 45 min | Not scheduled
M1 | Scope and positioning | Agree what Lab 8 is for, its deadline, and what the demo leads with. | Q1, Q9, Q11, Q14 | Lab 8 programme owner; Acies GTM or practice lead; Guna | pitch.md; Report 3 |  | 60 min | Not scheduled
M2 | Metrics, data and decision rules | One revenue baseline, the six KPIs, unsupported cards, and one decision vocabulary. | Q2, Q3, Q4, Q5, Q6, Q13 | Programme owner; FMCG or finance SME; Guna | Report 1; Gap Analysis tab |  | 60 min | Not scheduled
M3 | Tabs and personas sign-off | Approve the five domain tabs and what each persona sees. | Q7, Q8 | Programme owner; UX / design; persona representatives if available; Guna | Report 2; Personas & Journey tab |  | 45 min | Not scheduled
M4 | Delivery and infrastructure | Hosting, LLM budget, and what agents may do on their own. | Q10, Q12, Q15 | Programme owner; infrastructure / IT; budget holder; Guna | Architecture Roadmap tab |  | 45 min | Not scheduled
M5 | Reverse KT with the previous team | Play back our understanding; close gaps on data origin, persona views and the real brand names. | — | Amita; SreeVyshnavi; acies-Jai / Jaiadithya A; Guna | Handover Findings tab |  | 60 min | Not scheduled
M6 | Weekly status | Walk this tracker; unblock anything Blocked or At risk. | As needed | Programme owner; project team | This tracker | Weekly | 30 min | Not scheduled
M7 | Demo dry run | Rehearse the demo end to end before a client sees it. | — | Programme owner; one VP-level reviewer | Personas & Journey tab (section C) |  | 60 min | Not scheduled

## Gap Analysis
Gap Analysis — requirements backlog
The team's functional reviews, carried verbatim (Research_doc/…Project_Tracker 1.xlsx). 'Plan step' and 'Our note' are added. Profitability, SKU Rationalization and Signals have no review yet.
# | Module | Area | What the existing solution shows | Gap | Recommended improvement | Decision supported / business impact | Validation needed | Team status | Plan step | Our note
1 | Portfolio Health | Executive KPI layer | Net Sales $480M; Avg Gross Margin 38.47%; Revenue Concentration 27.81%; Long-tail SKU Burden 66.7%; second KPI row includes Revenue, SKU Count, Growth, Orders Today, Forecast Attainment. | Strong executive KPI coverage, but the KPI hierarchy mixes strategic portfolio metrics with operational metrics. 'Orders – Today' may be useful operationally but should be validated as a VP portfolio-health KPI. | Separate Strategic Portfolio KPIs from Operational Signals. Consider Portfolio Revenue vs Target, Gross Margin vs Target, Revenue at Risk, Portfolio ROI/Contribution, Long-tail Burden, and Growth. Move Orders Today to an operational/signal layer if not decision-critical. | What requires executive attention at portfolio level today? | Validate KPI ownership and executive use cases. | Potential Gap – Validate | 3.2
2 | Portfolio Health | KPI targets & variance | Several cards show TARGET, but some target fields display '-' while others have explicit targets such as $900M, 100 SKUs, 10%, 5000, 97%. | Target availability is inconsistent. A KPI without a defined target cannot reliably indicate health or trigger action. | Define target, benchmark and tolerance for every strategic KPI. Show Actual / Target / Variance / Trend consistently. | Are we on track against the agreed portfolio objectives? | Confirm target source, period and tolerance by KPI. | Needs Business Validation | 2.3
3 | Portfolio Health | Portfolio Health Score | 88% HEALTH with 'OPTIMAL / ON-TRACK' and a statement about high-margin cash cows and growing products. | The overall score is decision-friendly but its composition is not visible. Users cannot easily see which dimensions produced 88%. | Add score decomposition: profitability, growth, concentration, lifecycle, complexity, risk, customer/market health and supply/service. Show weights, thresholds and top positive/negative drivers. | Why is portfolio health 88%, and what could change it? | Validate scoring model, weights and thresholds. | Potential Gap – Validate | 3.2
4 | Portfolio Health | Lifecycle Journey | 119 SKUs reconcile across Introduction 7, Growth 37, Maturity 54, Decline 21. Revenue shown by stage totals $10,592M. | Lifecycle view is useful for portfolio shape and stage efficiency. It primarily describes where products are; it does not explicitly prescribe what to do. | Add stage-specific actions: invest, scale, defend, optimize, reposition, harvest or sunset, with revenue/margin/risk implications. | Where should we invest or intervene across the lifecycle? | Validate lifecycle rules and action playbooks. | Potential Gap – Validate | 3.2
5 | Portfolio Health | Lifecycle efficiency | Growth is labeled Most Efficient; Decline Least Efficient with ratios 112.5 and 48.0. | The ratio formula and business meaning are not visible. Users may not know whether the ratio represents revenue/SKU, margin/SKU, growth efficiency or another measure. | Expose ratio definition, formula, benchmark and interpretation. Allow drill-down to products causing stage inefficiency. | Which lifecycle stage creates or destroys the most value? | Confirm formula and benchmark logic. | Needs Logic Validation | 2.3
6 | Portfolio Health | Portfolio data reconciliation | Top cards show Net Sales $480M and Portfolio Revenue $1,071.1M; lifecycle section shows Total Revenue $10,592M. Product examples show revenues such as $137.38M. | These figures may represent different scopes, periods, currencies or aggregation levels, but the screenshot does not make the distinctions clear. | Add period, currency, scope and data-source labels. Reconcile portfolio totals with lifecycle, matrices and SKU-level views or clearly explain why they differ. | Can executives trust that all portfolio views use consistent data? | Perform data reconciliation across all displayed revenue metrics. | Critical Validation | 3.1c | Confirmed 22 Sep: the lifecycle 'Total Revenue' sums a per-SKU field that is not in $M (LifecycleHealthPanel.tsx:100) — about 22× actual net sales. See R18.
7 | Portfolio Health | Portfolio SKU Count | 119 SKUs; target 100; trend says -3 SKUs rationalized. | Good context for complexity, but SKU count alone does not indicate whether rationalization created value. | Pair SKU count with gross margin contribution, revenue retained/lost, complexity cost removed, working capital released and service/customer impact. | Did SKU rationalization actually improve the portfolio? | Validate rationalization outcome metrics. | Potential Gap – Validate | 3.2 | The dataset has 119 SKUs; the target of 100 is authored, not derived.
8 | Portfolio Health | Long-tail SKU Burden | 66.7% and note '68 SKUs <1% REV'. Long-tail view also uses bottom 70% and says 18 long-tail items consume massive supplier overhead. | The screen identifies a long-tail problem, which is valuable. However, revenue-only screening can miss strategically important low-volume products and operational complexity drivers. | Add margin, cost-to-serve, supplier count, component/commonality, changeovers, inventory, customer/channel dependency and strategic role before recommending pruning. | Which SKUs are truly value-dilutive versus strategically necessary? | Validate long-tail definition and strategic-exception rules. | Potential Gap – Validate | 2.3 | Report 1 also found this metric structurally inflated: the mean SKU share (0.84%) is below the 1% threshold, so an average SKU counts as long tail.
9 | Portfolio Health | Investment vs Return Margin Map | Products are segmented into Quick Wins, Strategic, Niche and Avoid/High Risk; investment is on x-axis and return margin on y-axis; approval action is available. | This supports capital allocation, but 'return' and decision thresholds need clearer definitions. A margin percentage alone may not capture absolute value, payback or risk. | Use incremental ROI/NPV/payback or contribution where appropriate; show investment, incremental revenue, margin contribution, risk, time-to-value and scenario outcome. | Where should incremental investment go? | Validate return definition and investment decision methodology. | Potential Gap – Validate | 3.2
10 | Portfolio Health | Investment approval workflow | Cards include Review Metrics and Approve Investment; portfolio also has an Executive Approval Board with meeting/reminder actions. | Approval is present, but the decision record and governance trail are not evident from the screenshots. | Add recommendation, rationale, financial case, risk, owner, approver, decision date, conditions, approval/rejection, and audit history. | Can an executive make and track a defensible investment decision? | Validate approval governance and audit requirements. | Potential Gap – Validate | 3.2
11 | Portfolio Health | Revenue vs Performance Matrix | Portfolio is segmented into High Performers, Underperformers, Hidden Growth and Attention Required; product cards have Authorize Strategy. | Useful segmentation, but the underlying Performance Score is not explained. The labels may hide multiple metrics. | Show performance score decomposition: growth, margin, forecast attainment, service, customer/market signals, etc. Define quadrant thresholds and recommended actions. | Which products deserve investment, intervention or repositioning? | Validate score formula and quadrant rules. | Potential Gap – Validate | 3.2
12 | Portfolio Health | Portfolio Alerts | Four brand alerts show percentages (92%, 85%, 87%, 89%); header says 2 Critical. | Alerts are actionable via Review, but the meaning of the percentage and why two are critical is unclear from the screen. | Use explicit alert semantics: severity, trigger, metric, threshold, trend, business impact, owner and recommended action. Ensure critical count reconciles with alert list. | What needs immediate intervention and why? | Validate alert scoring, severity and count logic. | Needs Logic Validation | 3.2
13 | Portfolio Health | Executive Approval Board | Three pending items include SKU rationalization, compliance certification and launch readiness criteria, with wait times. | This is useful as an action queue, but items span different decision types and lack visible business impact/context. | Prioritize by value at risk, decision deadline, financial impact, customer impact and risk. Add recommended decision and dependencies. | Which pending decision should the executive address first? | Validate prioritization criteria and workflow states. | Potential Gap – Validate | 3.2
14 | Portfolio Health | Pareto SKU Concentration | Top 10%, Top 30%, Bottom 70% views; top 10% 26.4% sales and top 30% 60.4%; long-tail insights. | Strong concentration analysis, but revenue concentration alone does not identify optimal portfolio actions. | Extend Pareto with gross margin, contribution, complexity cost, inventory, supplier/component dependency and strategic/customer role. Link candidates directly to rationalization simulation. | Where is concentration creating risk or opportunity? | Validate additional dimensions and action linkage. | Potential Gap – Validate | 3.2
15 | Portfolio Health | Rationalization linkage | Approval item proposes Phase 1 sunset of 15 low-margin tail products. | The dashboard surfaces rationalization decisions, but the visible Pareto/long-tail views do not show a quantified before/after business case for the 15 SKUs. | Connect candidate selection to a rationalization simulator: revenue at risk, margin gain, inventory release, supplier/complexity savings, customer impact and replacement options. | Which SKU set should be removed to maximize value with minimum downside? | Validate rationalization model and exception handling. | Strategic Enhancement | 3.5
16 | Portfolio Health | Strategic exceptions | Low-volume/long-tail products may still have strategic roles, but no explicit exception mechanism is visible. | Revenue-based pruning can incorrectly target products that support key customers, channels, geographies, bundles or future platforms. | Add strategic-role flags and exceptions: anchor customer, channel requirement, regulatory need, bundle dependency, innovation role, platform dependency. | Which low-performing SKUs must be retained and why? | Confirm strategic exception taxonomy. | Potential Gap – Validate | 2.5
17 | Portfolio Health | Scenario / What-if portfolio planning | Investment map has capital allocation actions and rationalization is referenced, but an integrated portfolio scenario comparison is not visible. | Portfolio health is largely descriptive. A stronger decision cockpit would allow leaders to test actions before approving them. | Enable scenarios such as invest, price change, discontinue, launch, reposition, bundle, or increase/decrease distribution, with revenue, margin, SKU count, complexity and risk impact. | What happens to the portfolio if we take this action? | Validate required scenario levers and business rules. | Strategic Enhancement | 3.2
18 | Portfolio Health | Cross-functional root cause | Portfolio Health contains financial, lifecycle and operational-style indicators. | The screen can identify where performance is weak, but root causes may sit in supply, pricing, customer, quality, market or product complexity. | Link portfolio exceptions to Profitability, Signals, Launch Readiness and SKU Assortment so the user can move from symptom to cause to action. | Why is the portfolio/product underperforming? | Validate cross-tab navigation and ownership. | Strategic Enhancement | 3.7
19 | Portfolio Health | Action-to-impact tracking | Review, Approve Investment, Authorize Strategy, Schedule Meeting and Remind Later actions are visible. | Actions are present, but closed-loop measurement of approved decisions is not visible. | Track approved action → owner → due date → expected impact → actual impact → variance → corrective action. | Did the decision deliver the expected value? | Validate action tracking and benefit-realization process. | Potential Gap – Validate | 2.1
20 | Portfolio Health | External/customer context | The current screens are primarily internal performance and portfolio analytics. | Portfolio decisions can be incomplete if customer needs, competitive moves and market signals are not incorporated. | Connect market/VoC signals, competitor changes and customer demand signals to affected products and portfolio decisions. | Should we invest, reposition or retire based on market/customer evidence? | Validate external-data availability and signal governance. | Strategic Enhancement | 3.6
21 | Portfolio Health | Continuous portfolio governance | The dashboard presents a current portfolio state. | A portfolio should be actively governed over time rather than reviewed only as a static dashboard. | Add recurring portfolio review cadence, decision history, threshold changes, realized benefits and portfolio drift monitoring. | Is portfolio health improving and are decisions preventing complexity from returning? | Validate governance cadence and review ownership. | Potential Gap – Validate | 4.8
22 | Launch Readiness | New SKU Brief | Captures SKU name, category, projected revenue, gross margin, lead time, promotion budget, supplier count, distribution channels, current stage, budget and spend. Current: Basic launch inputs are captured for readiness evaluation. | Validating whether all business-critical launch factors are represented. | Validate and enrich inputs with relevant demand forecast, supply capacity, quality/regulatory readiness, inventory availability and customer/channel commitments, based on business requirements. | More comprehensive launch-readiness assessment. | Validate required launch inputs with business/product team. | Open | 3.3
23 | Launch Readiness | Readiness Scoring | Overall Launch Readiness score is calculated for the SKU. Current: A single readiness percentage is presented. | The score does not immediately explain why the SKU received the score or which factors drive it. | Provide dimension-level scores, weights, thresholds and key drivers behind the overall score. | Improves transparency and supports corrective action. | Validate scoring methodology, weights and thresholds. | Open | 3.3
24 | Launch Readiness | Readiness Radar | SKU is compared with category benchmark across Market Fit, Supply Readiness, Margin Health, Channel Coverage and Risk Profile. Current: Radar comparison shows SKU versus benchmark. | Benchmark gaps do not clearly translate into specific actions. | Add Benchmark Gap → Root Cause → Recommended Action logic. | Converts benchmarking into actionable insight. | Validate benchmark definitions and action rules. | Open | 3.3
25 | Launch Readiness | Risk Profile Analysis | Key risk drivers such as lead time and promotion budget pressure are displayed. Current: Risk drivers are identified in the analysis section. | Relationship between each risk driver and business/financial impact is not sufficiently visible. | Link risk drivers to revenue at risk, margin impact, launch delay or additional cost. | Helps decision-makers understand the consequence of each risk. | Validate risk-to-impact calculation rules. | Open | 3.3
26 | Launch Readiness | Revenue at Risk | Revenue at Risk Exposure is displayed as a financial risk metric. Current: The screen provides a revenue-at-risk value. | Need to validate how the value is calculated and how it reconciles with identified risk drivers. | Show calculation logic/driver explanation and contribution of each risk to total exposure. | Builds confidence in the risk assessment. | Validate Revenue at Risk formula and source data. | Open | 2.3
27 | Launch Readiness | Risk Mitigation & Cost Simulator | A SKU Risk Mitigation & Cost Simulator provides baseline versus simulated views. Current: Simulation capability is already present. | Need to validate what mitigation actions can actually be selected and how their impact is calculated. | Introduce explicit mitigation actions such as alternate supplier, expedited logistics, additional inventory, marketing adjustment or launch-date change, where applicable. | Enables evaluation of corrective actions before committing resources. | Understand current simulator rules and supported actions. | Open | 3.3
28 | Launch Readiness | Baseline vs Simulated | Baseline and simulated states are compared in the simulator. Current: Spend/risk comparison is shown. | The simulation may not expose the complete business trade-off across operational and financial KPIs. | Compare Readiness, Revenue at Risk, Revenue, Margin, Cost, Inventory, Launch Date and Risk Level before versus after simulation. | Provides a complete scenario impact view. | Validate required scenario output KPIs. | Open | 3.3
29 | Launch Readiness | Scenario Comparison | Mitigation simulation is available. Current: A simulated state can be reviewed against baseline. | Need to validate whether multiple mitigation strategies can be compared side-by-side. | Introduce Scenario A/B/C comparison and allow users to identify the preferred scenario. | Supports structured trade-off decisions. | Validate business need for multi-scenario comparison. | Open | 3.3
30 | Launch Readiness | Launch Milestones | Supplier Onboarding, Channel Agreements, Production Trials, Distribution Setup, Marketing Campaign and Launch Go-Live are tracked. Current: Milestone completion percentage and status are visible. | Progress does not clearly indicate whether an incomplete milestone will impact the launch date. | Introduce milestone dependencies, critical path and expected launch-date impact. | Identifies activities that can genuinely delay launch. | Validate milestone dependencies and sequencing. | Open | 3.3
31 | Launch Readiness | Milestone Tracking | Milestones show statuses such as Completed/In Progress and completion percentage. Current: Progress is visually tracked. | A 50% or 85% completion value does not itself indicate launch risk. | Add planned date, expected/actual date, dependency, owner, delay and impact on Go-Live. | Converts progress tracking into launch-risk management. | Validate milestone dates, ownership and dependency data. | Open | 3.3
32 | Launch Readiness | Launch Decision | Overall Launch Readiness is represented as a percentage. Current: The user receives a readiness score such as 79%. | A percentage alone does not directly answer whether the SKU should launch. | Introduce GO / CONDITIONAL GO / NO-GO with conditions that must be resolved. | Creates a clear executive decision mechanism. | Validate decision gates and minimum readiness criteria. | Open | 2.5 | Needs one decision vocabulary first (Q13).
33 | Launch Readiness | Cost & Risk Impact | Project Budget, Spent Cost and Spent-to-Budget Ratio are displayed. Current: Cost consumption is visible. | Relationship between additional mitigation cost and risk reduction is not fully evident. | Show Incremental Mitigation Cost vs Risk Reduction vs Financial Exposure Avoided. | Supports cost-benefit justification for mitigation spending. | Validate financial impact and mitigation cost model. | Open | 3.3
34 | Launch Readiness | AI Forecast / Recommendation | AI Forecast section provides a message regarding sourcing and logistics risk. Current: AI-generated insight/recommendation is displayed. | Recommendation needs stronger explainability regarding why it was generated and what evidence supports it. | Show Recommendation → Reason → Supporting Metrics → Expected Impact → Confidence → Suggested Action. | Improves trust and usability of AI recommendations. | Validate AI methodology and explainability requirements. | Open | 4.2 | The recommendation text is authored; no model is called today (H11).
35 | Launch Readiness | Category Benchmark | SKU performance is compared against category benchmark averages. Current: Benchmark provides a reference point. | Benchmark gap may not distinguish acceptable from unacceptable performance. | Introduce configurable Green / Amber / Red thresholds and business-specific benchmark rules. | Enables faster identification of launch blockers. | Validate benchmark thresholds with business. | Open | 2.5
36 | Launch Readiness | Launch Lifecycle | Launch milestones are tracked through Go-Live. Current: The visible process focuses on readiness and launch execution. | Post-launch performance feedback is not visible in the current solution. | Connect launch readiness with post-launch actuals such as sales, margin, forecast accuracy, service level and launch performance. | Creates a closed-loop learning process for future launches. | Validate post-launch data availability and ownership. | Open | 3.3 | Needs launch dates — 0 of 119 SKUs have one (Q3).
37 | Cross-module | Cross-module investigation | Information exists across capabilities. | Insight → Diagnosis may require manual correlation. |  |  | Can users move seamlessly across Health, Profitability, Signals and Rationalization? | To validate | 3.7
38 | Cross-module | Actionability | The user may see what is happening but still need to determine what to do. | Insight → Recommendation → Action. |  |  | Does the solution clearly guide the next business action? | To validate | 2.1
39 | Cross-module | Explainability | Scores/recommendations may need clearer drivers and evidence. | Score → Drivers → Root Cause → Action. |  |  | Can users understand why the score/recommendation was generated? | To validate | 2.1
40 | Cross-module | Strategic SKU context | Financial performance alone may not capture customer/channel/market importance. | Performance → Strategic Context → Decision. |  |  | What exceptions are considered before rationalization? | To validate | 2.5
41 | Cross-module | Signal-to-action | Signals may require additional investigation to assess impact. | Signal → Impact → Decision → Action. |  |  | What happens after a signal is identified? | To validate | 3.6
42 | Cross-module | Launch decision | Readiness dimensions exist; final decision criteria need validation. | Assessment → GO / Conditional GO / NO-GO. |  |  | Does readiness clearly support the launch decision? | To validate | 2.5
43 | Cross-module | Decision-to-impact | Post-approval ownership and benefits need validation. | Decision → Action → Outcome → Benefit. |  |  | Can expected vs actual impact be measured? | To validate | 2.1
44 | Cross-module | Metric lineage | Important metrics may require clearer definitions and traceability. | Source → Calculation → Metric → Decision. |  |  | Can users trace key metrics to source, logic and owner? | To validate | 3.1c | Same root problem as H8 — fixed by one metric registry (3.1c, 3.8).

## Personas & Journey
Personas & Journey
Sections A and B are the team's work, verbatim. Section C transcribes the team's Miro decision journey; its last column is our proposal, to confirm in M3.
A · Who needs which capability
Capability | VP Product Management | Product Manager | Pricing & Margin Partner | Primary decision
Portfolio Health | Primary | Secondary | Secondary | Where should we invest, intervene or exit?
Launch Readiness | Secondary | Primary | Secondary | Should the product launch, and what is blocking it?
Profitability | Primary | Primary | Primary | Where is margin leaking and how can profitability improve?
SKU Rationalization | Secondary | Primary | Primary | Which SKUs should be retained, optimized, repositioned or sunset?
Signals | Primary | Primary | Secondary | What changed and what requires attention?
Decision Intelligence & Orchestration | Primary | Primary | Primary | What should we do, why, what-if, who approves, and what impact will result?
B · Current → future decision journey
Capability | Current process / pain point | Future capability | Future decision | Business outcome
Portfolio Health | User investigates portfolio issues manually | Detect + Diagnose + Correlate | Recommendation | Faster, evidence-based decision
Launch Readiness | Manual comparison of readiness, risk and benchmarks | What-if + AI Recommendation | Approval | Faster and lower-risk launch decision
Profitability | Manual root-cause analysis across financial drivers | Explainable Decision Support | Corrective Action | Improved margin and profitability
SKU Rationalization | Manual business assessment of SKU performance | Scenario Comparison | Retain / Optimize / Reposition / Discontinue | Optimized portfolio and reduced complexity
Signals | User manually connects signals with portfolio evidence | Prioritize + Orchestrate | Action | Faster response to market/customer changes
C · End-to-end decision journey (team's Miro board)
# | Stage | What happens | Screens involved today | Proposed home in the 5-tab target (confirm in M3)
1 | Business / portfolio need | A question or trigger arrives | — | Outside the app
2 | Business inputs | Data is consolidated into the solution | — | Data layer (warehouse + API)
3 | Home | The user opens the solution | Home | Landing summary inside Portfolio Health (Report 2)
4 | User investigates | Three detection paths | Portfolio Health · Profitability · Signals Board | Tabs: Portfolio Health, Profitability Tree, Market & VoC Signals
5 | Identify problem | Decision point: is there a problem? | Alerts on several screens | Exceptions and alerts within each tab
6 | Top-Down Drill | Drill into the cause | Top-Down Drill | A drill-down inside each tab — not a tab of its own
7 | Root cause / evidence | Evidence for the cause | Audit drawer | Audit drawer and explanation panel
8 | Business assessment | Evaluate the options | — | —
9 | Decide an option | Three decision paths | SKU Rationalization · SKU Assortment · Launch Readiness | Tabs: SKU Rationalization, Launch Readiness. Where Assortment goes is to be settled — Report 2 folds it into Portfolio Health.
10 | Scenario / simulation | Model the option | Simulators in several tabs | Simulator within the deciding tab
11 | Financial / business impact | Quantify it | Partly | Impact panel alongside the simulator
12 | Decision / approval | Submit and approve | Approval buttons on several screens | One approval flow
13 | Action | Carry out the decision | Task Tracker | Task list in the header (Report 2)
14 | Impact measurement | Track the outcome and close | Not built | Closed loop — see Gap Analysis 'Action-to-impact tracking'
Miro board | Open the decision journey

## Risks & Issues
Risks & Issues
Risk = might happen · Issue = already happening. Severity is a formula from Impact × Likelihood.
ID | Type | Risk or issue | Consequence | Impact | Likelihood | Severity | Owner | Mitigation / next step | Linked | Status
R1 | Risk | Scope unresolved — capability demo or competing product | Wrong investment; rework | High | High |  | Programme owner | Hold M1; proceed on default A meanwhile | Q1 | Open
R2 | Issue | Conflicting figures on screen ($473M vs $851M revenue; 38.55% vs 36.2% margin) | Demo credibility | High | High |  | Guna | Metric registry; wire the computed arrays | Q2, 3.1c | Open
R3 | Issue | Profit cards have no cost basis (no opex data) | An undefendable number in front of a client | High | High |  |  | Remove the cards unless opex is added | Q4 | Open
R4 | Issue | Two required KPIs cannot be computed (no launch dates) | Brief not met | High | High |  |  | Synthetic launch table | Q3 | Open
R5 | Issue | Real brands in demo data (seven in the database, plus PepsiCo brands) | Trademark or brand complaint | High | Medium |  |  | Rename to fictional brands | Q8, 3.1d | Open
R6 | Issue | Netherlands margin inverted against the source | Credibility with an informed viewer | Medium | Medium |  |  | Generator constraint plus a validation check | Q6 | Open
R7 | Risk | Database password in pushed git history (a3a3c54) | Credential exposure | Medium | Low |  | Guna | Rotated; never reuse; confirm repository visibility | Q12 | Mitigated
R8 | Issue | Local PostgreSQL accepts connections without a password ('trust') | Any local user can connect as superuser | Low | Medium |  | Guna | Switch to scram-sha-256, then strengthen the app password | — | Open
R9 | Risk | No demo date set | No forcing function; scope drifts | High | Medium |  | Programme owner | Set a date in M1 | Q9 | Open
R10 | Risk | Backend (6 weeks) is the critical path | Demo slips | High | Medium |  |  | Narrow the API to Next-state endpoints; start once the KPI framework is agreed | 3.8 | Open
R11 | Risk | Knowledge concentrated in one contributor — all commits since 1 Sep | Single point of failure | Medium | Medium |  |  | CLAUDE.md, this tracker, pairing | — | Open
R12 | Risk | Work tracker and architecture diagrams not in version control (gitignored) | Lost on a fresh clone | Medium | Medium |  | Guna | Remove from .gitignore; use this sheet as the shared tracker | — | Open
R13 | Risk | About 30 files of completed work are uncommitted | Loss of work | High | Low |  | Guna | Commit in logical chunks (do not push until R7 is closed) | — | Open
R14 | Issue | Smoke test covers 9 of 12 tabs | Breakage in tabs 9–11 goes unnoticed | Medium | Medium |  |  | Extend the test to all tabs | 4.3 | Open
R15 | Risk | LLM model and pricing assumptions are out of date | Wrong running cost quoted | Medium | Medium |  |  | Re-price before quoting | Q10 | Open
R16 | Issue | Stale documentation — SKU counts disagree across documents | Wrong numbers repeated | Low | High |  |  | Correct the documents; treat them as dated | — | Open
R17 | Issue | Six npm security advisories in build tooling | Development-only exposure | Low | Low |  |  | Apply non-breaking npm audit fixes | — | Open
R18 | Issue | Lifecycle 'Total Revenue' shows ~$10,592M — about 22× actual net sales | Executives see a revenue figure an order of magnitude too high | High | High |  | Guna | Fix LifecycleHealthPanel.tsx:100; route through the metric registry. Found by the team's review. | 3.1c | Open
R19 | Issue | Five competing project plans across the team | People track against different lists; status disagrees | Medium | High |  |  | Adopt this merged tracker (M8); retire the others | D13 | Open
R20 | Issue | Team benchmark compares PLM vendors with mixed scales; sources unverified | Weak external comparison | Low | Medium |  |  | Use Report 3 externally; verify sources; one rating scale | 1.5 | Open
R21 | Risk | Tab rework (3.2–3.6) has no estimates | Gate 3 and the demo date are optimistic | Medium | High |  |  | Estimate from the gap analyses in M8 | 3.2–3.6 | Open
R22 | Issue | Timeline selector fabricates variance on every figure, including the two KPI-strip metrics previously found to be genuinely computed | Changing the date-range filter changes numbers for reasons unrelated to the real period -- including '$473M', which is perturbed by a deterministic hash even at the default 12-month view | High | High |  | Guna | Remove the noise layer (utils/timeframe.ts) once the metric registry (3.1c) is the single source; until then, treat every displayed figure as unverified whenever the timeline filter is not left at its default | 3.1c | Open

## Decisions
Decisions — already made
Add new decisions as they are taken, including answers from Open Questions.
# | Date | Decision | Why | Alternatives considered | Decided by | Revisit if
D1 | ~9 Sep 2026 | Build a synthetic dataset | No transaction-level data was available — only aggregate findings. | Wait for real data; keep hardcoded figures | Project team | Real client extracts become available
D2 | By 14 Sep 2026 | Report in US dollars only | Simplicity; European figures treated as already converted. | Multi-currency with an FX table | Guna | A client needs local currency
D3 | 14 Sep 2026 | PostgreSQL star schema of 13 tables | Relational integrity and metrics in SQL. | S3 + Parquet + DuckDB (earlier proposal) | Project team | Analytics outgrow PostgreSQL
D4 | ~14 Sep 2026 | Do not force the 34/16/16/34 segment split | With median splits on both axes it is mathematically unreachable. | Bias the generator | Project team | —
D5 | 17 Sep 2026 | Target five domain tabs | The Lab 8 brief requires exactly five. | Keep 12 | Brief (binding) | —
D6 | 20 Sep 2026 | Backend in Python / FastAPI | The data layer is already Python. | Node / Express | Guna | —
D7 | 20 Sep 2026 | Delete the unused Express server and dependencies | Nothing used them; contradicted D6. | Keep as an API seed | Guna | —
D8 | 20 Sep 2026 | Compute metrics in SQL — one implementation | Copies of a formula drift apart. | Compute in the API | Project team | —
D9 | 20 Sep 2026 | The LLM explains results; it never does arithmetic | Lower cost; reproducible numbers. | Let the LLM compute | Project team — to confirm (Q10) | —
D10 | 20 Sep 2026 | Pin Python dependencies exactly | The generator is deterministic. | Version ranges | Project team | —
D11 | 20 Sep 2026 | Non-superuser application database role | Least privilege. | Connect as postgres | Guna | —
D12 | 20 Sep 2026 | Keep the five unwired computed arrays as wiring points | Their values are correct. | Delete them | Project team | Once wired, remove the aliases
D13 | 22 Sep 2026 | Merge the team tracker and ours into one plan, with P1–P4 and Gates 1–4 as the backbone | Five plans were in circulation; the team tracker's problem-first structure suits stakeholder review. | Keep separate trackers | Proposed — confirm in M8 | —
D14 | 22 Sep 2026 | Assume no deadline; keep every date tentative and computed from durations | No deadline is set (confirmed 22 Sep); the 20-day figure is a placeholder. | Plan to 30 Sep | Guna | A demo date is set (Q9)

## Architecture Roadmap
Architecture Roadmap — from today to the target
Diagrams: documentation/system_architecture.md (Excalidraw-ready; not in git — see R12).
Sequence
Step | Change | Why in this order | Plan step |  | Status
1 | Load the dataset into PostgreSQL | Everything else reads from it. | 3.1a |  | Done
2 | Settle the baseline, KPI list and decision vocabulary (M2) | Registry and rules need one definition. | 1.7 |  | Not started
3 | Derived metrics and the 16 checks in SQL | One implementation per formula. | 3.1b |  | Not started
4 | Metric registry — one definition per figure | Structural fix for conflicting numbers. | 3.1c |  | Not started
5 | Wire the five unused computed arrays; fix the lifecycle revenue bug | Quick wins; no backend needed. | 3.1c |  | Not started
6 | FastAPI read endpoints over the registry | Makes the database reachable. | 3.8 |  | Not started
7 | One data hook in React; replace constant imports | A data swap, not a rewrite. | 3.9 |  | Not started
8 | Consolidate 12 tabs into 5, following the decision journey | Brief compliance. | 3.7 |  | Not started
9 | Checks and smoke test in CI, all 12 tabs | Catches regressions. | 4.3 |  | Not started
10 | Closed loop: decision → action → measured impact | The journey's final stage; not built. | 2.1, 4.8 |  | Not started
11 | Future: scheduled ingestion from ERP, POS, PLM, demand planning | Real data replaces synthetic. | 4.8 |  | Not started
12 | Future: orchestrator and five agents — the LLM explains, never computes | The AgenticBus proper. | 4.1, 4.2 |  | Not started
Component view — Now → Next → Future
| Component | Now | Next (trustworthy demo) | Future (target) | Plan step
| Source of figures | Compiled into the bundle; 2 of 7 computed arrays wired | PostgreSQL + metric registry | Same, fed by real extracts | 3.1c, 3.8, 3.9
| API | None | FastAPI read API | FastAPI gateway | 3.8
| Tabs | 12 | Consolidating to 5 | 5 domain tabs | 3.7
| Decision loop | Stops at approval buttons | Approve → act | Act → measure impact → learn | 2.1, 4.8
| Agents | Keyword matching | Unchanged | Orchestrator + 5 agents | 4.1, 4.2
| LLM | None | None | Explanation only, never arithmetic | 4.2
| Checks | 16 data checks; smoke on 9 of 12 tabs | Both in CI; all tabs | Plus data-quality gates | 4.3
| Hosting | Static frontend on Vercel | Plus API and database hosting | Production hosting | 4.7

## Research & Data
Research & Data — what we learned
Our research and the team's, side by side. Light yellow = please complete.
# | Item | Question it answered | What we found | What it changed | Link
R1 | KT on the existing application | What does the app do, for whom, from what data? | 3 personas, 12 tabs, 43 overlays; every figure hardcoded; no backend or database. | Remediation before new features.
R2 | Project blueprint and brief | What does the brief require? | Exactly 5 domain tabs, 6 required KPIs, 3 role lenses. Labs are GTM assets. | Defined the target state.
R3 | Report 1 · Metric Dictionary | What does every number mean? | 2 of 6 required KPIs computed; revenue and margin each have two baselines. | Metric integrity (3.1c); Q2–Q5. | Report 1 (Google Doc)
R4 | Report 2 · Twelve Tabs to Five | Is every tab worth keeping, per persona? | 12 tabs vs 5 required; duplicated persona views; PM may see the VP's launch view. | Consolidation (3.7); Q7. | Report 2 (Google Doc)
R5 | Report 3 · Worth Building? | Who are the incumbents? | Depends on positioning. Competing on data breadth is not winnable; on explainability it is. | Q1. | Report 3 (Google Doc)
R6 | Team review · Portfolio Health | Does Portfolio Health support executive decisions? | 21 gaps: KPI hierarchy and targets, unexplained health score, no stage-specific actions, revenue that does not reconcile (Critical), no what-if, no closed loop. | Requirements for 3.2; reconciliation → 3.1c. | Gap Analysis tab
R7 | Team review · Launch Readiness | Does Launch Readiness support a launch decision? | 15 gaps: a score without drivers, no GO / CONDITIONAL GO / NO-GO, milestones without dependencies, no multi-scenario comparison, no post-launch loop. | Requirements for 3.3; decision rule → 2.5, Q13. | Gap Analysis tab
R8 | Team · Persona × capability matrix | Who is primary for which decision? | VP primary for Portfolio Health, Profitability, Signals. PM primary for Launch Readiness, Profitability, SKU Rationalization, Signals. Pricing & Margin primary for Profitability and SKU Rationalization. | Evidence for Q7; the PM should get its own launch view. | Personas & Journey tab
R9 | Team · End-to-end decision journey | How does a user move from signal to decision? | Detect → diagnose (drill, root cause) → decide (Rationalization, Assortment, Launch) → simulate → approve → act → measure. | Demo script (4.5); consolidation logic (3.7). | Personas & Journey tab
R10 | Team · PLM benchmark | How does the product compare with PLM and portfolio tools? | Five vendors; differentiation claimed in SKU rationalization, assortment and market signals. | Complements Report 3; needs verified sources before external use. | Benchmark tab
R11 | Dataset search | Is there a transaction-level dataset we can use? | No — only aggregate outputs of a notebook analysis. | Generate our own (D1).
R12 | Other data sources reviewed | What else did we look at, and why did it fall short?
R13 | Synthetic dataset | Can we reproduce the known findings? | 119 SKUs × 7 countries × 4 channels × 731 days; 368,013 rows; seeded (20260909). | A real data spine.
R14 | Validation | Does it match the source? | 16 of 16 targets met: $473.0M net sales, +8.29% growth, 38.55% margin — confirmed after loading. | Confidence.
R15 | Known data gaps | What can the data not support yet? | No launch dates (0 of 119); no opex; Netherlands margin inverted; no competitor or VoC feed. | Q3, Q4, Q6, Q11.

## Handover Findings
Handover Findings — the condition of what we received
Measured, not estimated. Doubles as the agenda for reverse KT (M5).
# | Area | What we found | Evidence | Why it mattered | What we did | Status
H1 | Repository hygiene | 144 tracked files in the root — scratch scripts, text dumps, duplicated HTML and PDF — plus .gemini/ (38) and extracted_tabs/ (6). | git ls-files | Hard to tell product code from debris. | 187 files removed; the root holds 10 tracked files. | Done
H2 | Oversized files | Nine component files totalling 22,619 lines; the largest 3,981. | Line counts | Slow to change and easy to break. | Split into 30 modules, 11,854 lines (−47%). | Done
H3 | Dead code | About 3,500 lines never executed, including PortfolioHealthMapOld (1,289) and 10 orphaned components. | Import graph | Misled an early audit of what each persona sees. | Removed. | Done
H4 | Styling defects | 1,237 invalid Tailwind colour classes across 63 files. | Commit, 1 Sep | Colours silently not applied. | Fixed. | Done
H5 | Type safety | Type checking had been bypassed. | Commit, 1 Sep | Errors surfaced only at runtime. | Restored. | Done
H6 | No data layer | No dataset, database or API; every figure hardcoded. | Zero network calls in src/ | Numbers could not be audited or refreshed. | Dataset generated and loaded; API not yet built. | In progress
H7 | Missing source data | Original figures came from a notebook analysis; no transaction-level data was handed over. | Comments in data.ts | Metrics could not be computed or checked. | Built a calibrated synthetic dataset. | Done
H8 | Conflicting figures | Revenue $473M vs $851M; margin 38.55% vs 36.2%; rationalize candidates 46 vs 35; tail risk 15.79% vs 27.08%. | Report 1 | Undermines credibility in a demo. | Diagnosed; fix planned (3.1c). | Open
H9 | Designed but empty metrics | 20 metric labels styled; only 8 have a value. | KPICard.tsx vs data.ts | Empty KPI strips on four tabs. | Planned (3.1c). | Open
H10 | Navigation overload | 12 tabs against a brief requiring 5; VP and standard duplicates. | Report 2 | Brief not met. | Consolidation planned (3.7). | Open
H11 | Simulated AI | The agent widget matches keywords and simulates typing. | Agent widget code | The demo implies AI it does not perform. | Planned (4.2). | Open
H12 | Dead backend and unused dependencies | Express server nothing started; unused packages; vite declared twice. | package.json | Confused the architecture. | Removed; backend decided as Python / FastAPI. | Done
H13 | Real brands in demo data | Seven real brands in the SKU list; PepsiCo brands in the pricing simulator. | Database; SignalsBoard.tsx | Trademark exposure. | Planned (3.1d). | Open
H14 | Stale documentation | SKU count given as 102, 100, 120 and 240+; the real figure is 119. | Documents | Wrong numbers get repeated. | Corrected in CLAUDE.md. | Open
H15 | Revenue units bug | The lifecycle panel sums each SKU's 'rev' field and labels it $M: ~$10,592M against $473M actual. | LifecycleHealthPanel.tsx:100 — found by the team's review | Executives see revenue about 22× too high. | Confirmed 22 Sep; fix planned (3.1c). | Open

## Timeline
Timeline — from handover to today
Reconstructed from git history and project files. Light yellow = please confirm.
When | Stage | Event | Detail | Source
18 May 2026 | Build — previous team | Repository started | First commit by acies-Jai. | git log
18 May – 27 Jul 2026 | Build — previous team | Application built | 369 commits from four contributors: Amita (149), SreeVyshnavi (143), acies-Jai (72), Jaiadithya A (5). | git log
16 Jun 2026 | Build — previous team | A replaced view is left in the code | PortfolioHealthMapOld becomes unreachable but stays in a live file — 1,289 dead lines until 20 Sep. | Code history
22 Jun 2026 | Build — previous team | Figures switched to US dollars | 'Currency conversion to dollars' (Amita). | git log
13 Jul 2026 | Build — previous team | Real brands added to the SKU list | Sprite, Coca-Cola, Thums Up, 'Foorti', Pulpy Orange, 5-Star and Munch in one commit. | git log
24 Jul 2026 | Build — previous team | Competitor tracker and PricingAI console | Adds a Pepsi / Mountain Dew price-elasticity simulator to the Signals Board. | git log
27 Jul 2026 | Handover | Last commit by the previous team | — | git log
27 Jul – 1 Sep 2026 | Handover | Repository idle | No commits for five weeks. | git log
| KT | One week of knowledge transfer | Enter the dates in column A. | Confirm
1 Sep 2026 | Remediation | Current team's first commits | Type checking restored; bundle split; 1,237 invalid colour classes fixed; 43 overlays moved onto shared components. | 3 commits
3 Sep 2026 | Initiation | Project start (per team tracker) | Team tracker records 20 planned working days — a placeholder. | Team tracker
~9 Sep 2026 | Data | Dataset search comes up short | Only aggregate outputs of a notebook analysis were available. Decision to generate our own (D1). | Research & Data tab
14 Sep 2026 | Data | Synthetic dataset generated and validated | 119 SKUs, 368,013 fact rows, 16 of 16 targets met. | Commit a3a3c54
17 Sep 2026 | Research | Three feasibility reports published | Metric Dictionary · Twelve Tabs to Five · Worth Building? | Links tab
20 Sep 2026 | Remediation | Codebase clean-up completed | 187 files removed; nine oversized files split into 30 modules; Express server and 124 npm packages removed. | TODO.md
20 Sep 2026 | Architecture | Current → target architecture drawn | Backend confirmed as Python / FastAPI. | system_architecture.md
20 Sep 2026 | Data | PostgreSQL warehouse live | 377,364 rows; reconciles to $473.0M, +8.29%, 38.55%. | Research & Data tab
21 Sep 2026 | Alignment | Stakeholder questions drafted | 12 open questions, each with a recommendation and a default. | documentation/pitch.md
22 Sep 2026 | Tracking | Team tracker reviewed; plans merged | The team's P1–P4 plan, gap analyses and persona work merged into this tracker. Lifecycle revenue bug confirmed. Deadline confirmed as not yet set. | This tracker
23 Sep 2026 | Frontend | Persona-specific sidebar ordering prototyped | Sidebar order now differs per role, sourced from the persona matrix; verified on all three roles by screenshot. Found and logged a real bug: role does not update from a hashchange after first load. Not committed. | App.tsx; TODO.md O10
23 Sep 2026 | Metric integrity | Every formula in the app catalogued | Python generator, SQL, and all 9 frontend tabs -- each formula marked real / real-formula-fake-input / fabricated. New finding: the timeline selector fabricates variance on every figure, including the two KPI-strip metrics previously thought genuinely computed. | documentation/formulas.md

## Benchmark
Competitive Benchmark — PLM / PPM vendors (team research)
Carried verbatim. Complements Report 3, which compares against FMCG intelligence vendors. Read the caveats before using it outside the team.
Capability | Our product | Planview | Oracle PLM | SAP PLM | Siemens Teamcenter | Salsify
Product lifecycle | ✅ | ✅ | ✅ | ✅ | Strong | Partial
Portfolio health | Strong potential | Strong | ✅ | ✅ | Partial | Partial
Product launch | Strong | Strong | Strong | ✅ | ✅ | Strong
Profitability | Strong potential | ✅ | ✅ | Strong | ✅ | Limited
SKU rationalization | Core | Partial | Partial | Partial | Partial | Partial
SKU assortment | Core | Partial | Partial | Partial | Partial | Strong-ish
Scenario simulation | Existing | Strong | ✅ | Strong in costing | Partial | Partial
Market/VoC signals | Core | Partial | Partial | Partial | Partial | Strong for digital shelf
AI recommendations | Agent Orchestrator | AI | AI | AI | AI | AI
Executive decision cockpit | Strong potential | Strong | Strong | Strong | Partial | Partial
Supply-chain integration | Potential differentiator | Partial | Strong | Strong | Strong | Integration
Engineering/PLM depth | Limited | Limited | Strong | Strong | Very strong | Limited
Caveats
• | Full PLM engineering is out of scope for this product (Overview → Scope), yet four of the five comparators are PLM systems.
• | Our product is rated on potential ('Strong potential', 'Core'); competitors on current capability — not like-for-like.
• | Three rating scales are mixed (✅ / Strong / Partial). The 'AI recommendations' row reads 'AI' for everyone.
• | Sources are vendor product pages. The Planview link points to Oracle's PLM page; Salsify has no source.
Positioning (team's diagram)
Product lifecycle | PLM (Siemens Teamcenter, SAP PLM, Oracle PLM) and portfolio management (Planview, Oracle) → Product Lifecycle & Portfolio Intelligence → Portfolio Health · Profitability · SKU Rationalization · Launch Readiness · Cost / Risk · SKU Assortment → Signals / AI agents → Decision / recommendation.

## Links
Links — every document, repository and the live demo
'In git?' matters: an untracked or gitignored file is lost on a fresh clone.
Document | What it covers | Date | Link / location | Also at | In git?
Report 1 · Metric Dictionary | Every metric defined | 17 Sep 2026 | Google Doc | Artifact | No
Report 2 · Twelve Tabs to Five | Per-persona tab audit | 17 Sep 2026 | Google Doc | Artifact | No
Report 3 · Worth Building? | Competitive landscape | 17 Sep 2026 | Google Doc | Artifact | No
Reports folder | Acies Portfolio Lab — Reports | — | Google Drive folder |  | No
Team tracker | Source of P1–P4, gap analyses, persona matrix, benchmark | 22 Sep 2026 | Research_doc/Product_Lifecycle_Portfolio_Intelligence_Project_Tracker 1.xlsx |  | Not yet committed
Decision journey (Miro) | End-to-end user decision flow | — | Miro board |  | —
Build brief | What exists, tech stack | Sep 2026 | Artifact |  | No
Data model | Tables, columns, keys | Sep 2026 | Artifact |  | No
Validation | Dataset validation results | Sep 2026 | Artifact |  | No
Stakeholder pitch | Reports and open questions | 21 Sep 2026 | documentation/pitch.md |  | Not yet committed
System architecture | Now / Next / Future diagrams | 20 Sep 2026 | documentation/system_architecture.md |  | Gitignored
Data model specification | 13 tables, types, keys | 14 Sep 2026 | documentation/data_model_specification.md |  | Yes
Project blueprint | Original research brief | — | Research_doc/Acies AgenticBus_ Product Lifecycle and Portfolio Intelligence Project Blueprint.docx |  | Yes
CLAUDE.md | Guidance for AI-assisted development | 20 Sep 2026 | CLAUDE.md |  | Not yet committed
TODO.md | Engineering work log | Live | TODO.md |  | Gitignored
Live demo | Deployed frontend | Live | Vercel |  | —
Repository (working fork) | Branch_G | Live | GitHub |  | —
Repository (upstream) | Previous team's repository | Live | GitHub |  | —